## Sheet1
WatchMyMovie App
Α/Α | Section | Task | Workload | Owners | Status | Estimated date | Completion date
1 | Login | Login / Logout / Sessions | 2d | Σοφία Ρίζου/ Δήμητρα Σιμορέλη | 100% | 21/11/2018 | 18/11/2018
2 | Login | Check if already logged in or not | 2h | Σοφία Ρίζου | 100% | 21/11/2018 | 18/11/2018
3 | Login | Encrypt password (MD5) on login | 1h | Σοφία Ρίζου / Δήμητρα Σιμορέλη | 100% | 21/11/2018 | 18/11/2018
4 | Login | Check for special characters on login form | 2h | Σοφία Ρίζου | 100% | 21/11/2018 | 2018-04-12
5 | Login | Admin login | 1d | t.b.d. | 0% | 21/11/2019 | -
6 | Register | Register Form / Session | 4h | Σοφία Ρίζου/Δήμητρα Σιμορέλη | 100% | 21/11/2018 | 18/11/2018
7 | Register | Check if all fields are filled | 1d | Σοφία Ρίζου/Δήμητρα Σιμορέλη | 100% | 21/11/2018 | 18/11/2018
8 | Register | Check if email structure is correct | 1h | Σοφία Ρίζου | 100% | 21/11/2018 | 18/11/2018
9 | Register | Check if user is already registered | 4h | Σοφία Ρίζου | 100% | 21/11/2018 | 18/11/2018
10 | Register | Encrypt password (MD5) on register | 1h | Σοφία Ρίζου/Δήμητρα Σιμορέλη | 100% | 21/11/2018 | 18/11/2018
11 | Register | Save fields to DB on register | 1h | Σοφία Ρίζου/Δήμητρα Σιμορέλη | 100% | 21/11/2018 | 18/11/2018
12 | Register | Check for special characters on register | 2h | Σοφία Ρίζου | 100% | 21/11/2018 | 2018-04-12
13 | Search | Search movie by name | 5d | Σοφία Ρίζου, Δήμητρα Σιμορέλη, Ji Chenyang | 100% | 2018-01-11 | 2018-01-11
14 | Search | Add movie to favorites | 3d | Σοφία Ρίζου, Ji Chenhyang | 100% | 21/11/18 | 18/11/2018
15 | Search | Delete movie from favorites | 3d | Σοφία Ρίζου, Ji Chenhyang | 100% | 21/11/18 | 18/11/18
16 | Search | Display movie details | 2d | Δήμητρα Σιμορέλη, Ji Chenyang | 100% | 21/11/18 | 18/11/18
17 | Search | Go to movie's IMDB page | 1h | Δήμητρα Σιμορέλη | 100% | 21/11/18 | 18/11/18
18 | Search | Show message if no result | 1d | t.b.d. | 0% | 2019-06-01 | -
19 | Search | Return from movie to search results | 3d | Σοφία Ρίζου, Δήμητρα Σιμορέλη, Ji Chenyang | 0% | 2019-06-01 | -
20 | DB | Connection to DB | 4h | Σοφία Ρίζου,Ji Chenyang | 100% | 20/10/2018 | 20/10/2018
21 | DB | Create DB | 1d | Σοφία Ρίζου | 100% | 20/10/2018 | 20/10/2018
22 | DB | Check if movie is in database on "add to favorites" | 3d | Ji Chenyang | 100% | 2018-01-11 | 2018-01-11
23 | DB | Add movie to database on "add to favorites" | 3d | Ji Chenyang | 100% | 2018-01-11 | 2018-01-11
24 | DB | Check if movie is in database on "delete from favorites" | 3d | Ji Chenyang | 100% | 2018-01-11 | 2018-01-11
25 | DB | Delete movie from database on "delete from favorites" | 3d | Ji Chenyang | 100% | 2018-01-11 | 2018-01-11
26 | UI/UX | Register | 2d | Δημήτρης Καμπάς | 50% | 2019-06-01 | -
27 | UI/UX | Login | 2d | Δημήτρης Καμπάς | 50% | 2019-06-01 | -
28 | UI/UX | Logout | 2d | Δημήτρης Καμπάς | 50% | 2019-06-01 | -
29 | UI/UX | Header | 2d | Δημήτρης Καμπάς | 80% | 2019-06-01 | -
30 | UI/UX | Front page | 2d | Δημήτρης Καμπάς | 50% | 2019-06-01 | -
31 | UI/UX | Wishlist | 2d | Δημήτρης Καμπάς | 50% | 2019-06-01 | -
32 | UI/UX | Movie Results | 3d | Δημήτρης Καμπάς | 0% | 2019-06-01 | -
33 | UI/UX | Movie Details | 3d | Δημήτρης Καμπάς | 0% | 2019-06-01 | -
34 | miscelaneous | About section | 1h | Δημήτρης Καμπάς | 75% | 2019-06-01 | -
35 | feature | Show all favorite movies of the selected genre | 5d | t.b.d. | - | 2018-06-01 | -
36 | feature | Performance metric: Satisfaction | 4d | t.b.d. | - | 2018-06-01 | -
37 | feature (optional) | Show 5 latest added movies | 5d | t.b.d. | - | - | -